## Sheet1
Sustainability Planning Outline
Gustavus Adolphus Physical Plant
Revised: May 13, 2009
|  | Fiscal Year | 2009 | 2010 | 2011-2015 | 2016-2020 | Remarks
Fossil Fuel Use
Energy Conservation
|  | Support College's "Presidents' Climate Commitment" | On-going | On-going | On-going | On-going
|  | Build New Academic Building to highest practical LEED standard | 50% design | Begin const? |  |  | Currently between Gold and Platinum
|  | Convert remaining incandescent lamps to compact fluorescent | @ 80% | @ 90%
|  | Lighting conversion in Lund Forum | Complete
|  | Lighting conversion in Lund Arena |  | Summer |  |  | Delayed by Arena floor replacement
|  | Lighting conversion in Lund Natatorium |  | Summer
|  | Lighting conversion in Lund Gymnastics Studio |  |  | Summer 2010
|  | Window replacement in Sohre and Pittman Halls |  | Summer
|  | Window replacement in North/Gibbs/Sorensen Halls |  |  | Summer 2010
|  | Window replacement in Old Main |  |  | 2011?
|  | Window replacement in Carlson Administration |  |  | w/ Project?
|  | Window replacement in various college houses |  |  | On-going
|  | Window replacement in remaining portions of College View | Complete
|  | Window replacement in remaining portions of Rundstrom |  | Summer
|  | Window replacement in remaining portions of Nobel Hall |  |  | Summer 2010?
|  | Lighting-schedule control in Lund Center | Complete
|  | Lighting-schedule control in Library |  | Summer
|  | Daylight-controls on street and walkway lighting |  | Summer
|  | Daylight harvesting in Lund Forum and Natatorium |  | Summer
|  | Daylight harvesting in Evelyn Young Dining Room |  | Summer
|  | Expand use of occupancy sensor lighting control | On-going | On-going | On-going
|  | Relamp all 32-watt fluorescent with 25-watt | @ 50% | @ 100%
|  | Replace remaining non-LED exit lights | @ 90% | @ 100%
|  | Replace "outlying" summer boiler capacity with high-efficiency boilers | Nobel, SFAM | SFAA
|  | Add parallel positioning at central boilers | @ 60% | + 20%
|  | Replace high-use motors with premium efficiency | On-going | On-going | On-going
|  | Retrofit motors with variable-speed drives | On-going | On-going | On-going
|  | Require "EnergyStar" equipment purchase | On-going | On-going | On-going | On-going
|  | Recommission building systems |  |  | 5 buildings/year
|  | Expand functionality (and upgrade) energy management system |  |  | 2011?
Shift to Renewable Fuels
|  | Develop 2 - 6 megawatt wind turbine capacity |  | Hopefully
|  | Support solar-heating demonstration project at Interpretive Center | @ 75% | Complete
|  | Recycle waste vegetable oil (biodiesel or space heat) |  | Re-establish
|  | Shift to renewable fueled vehicles | @ 15% | + 5% | + 5%/year
|  | Add solar hot-water heating at Lund Center |  | Investigate
|  | Replace central boiler capacity with renewable fuels |  | New Ac. Bldg.?
|  | Large-scale PV installation |  | Hopefully
Water Quality
Water Conservation
|  | Use best practices for maintaining turf grass | On-going | On-going | On-going | On-going | Reduced irrigation by 4-6 million gallons in 2009
|  | Replace all toilets greater than 1.6 gpf with 20-30% lower than code | @ 60% | @ 100% |  |  | Expected to reduce water consumption by 2-4 gallons in 2009
|  | Replace remaining washing machines to high performance | @ 95% |  |  |  | Significantly reduce water, water heating and drying
|  | Replace shower heads with 20-30% lower than code |  | @ 25% | @ 100% |  | Will reduce both water and water heating use
Develop alternative sources for irrigation (storm water, gray water, etc.)
Recharge Aquifers
|  | Expand use of west-campus storm water treatment ponds |  |  | Project-linked?
|  | Develop storm water treatment ponds on east portion of campus |  |  | Project-linked?
Surface Water Quality
|  | Use "dried distillers grain" or "corn gluten meal" on turf grass | @ 20 acres | + 10 acres | Add 5 acres/year
|  | Decrease use of synthetic fertilizers, herbicides and pesticides | On-going | On-going | On-going | On-going
Sustainable Materials and Practices
|  | Complete Custodial Department shift to "green" chemicals | @ 90%
|  | Support "Big Hill Farm" as source of local produce for Dining Service | @ .5 acre | + .5 acre
|  | Big Hill Farm Greenhouse? |  | Plan?
|  | Shift from paper towels to hand-dryers | @ 10% | + 20% | + 20%/year
|  | Use carpet tile rather than broadloom | @ 15%
|  | Develop on-campus food waste compost system | @ 200#/week | + 1000#/week | + 1000#/week |  | Pre-consumer waste is composted by Big Hill Farm
|  | Shift hillside plantings to native grasses |  | + 2 acres | + 2 acres/year
|  | Support Linnaeus Arboretum's "Coneflower Prairie" development | Planting | On-going | On-going | Established | Initial planting in fall of 2008 - additional seedlings to be added
|  | Pursue LEED Sustainable Operations certification | Investigate |  |  |  | Chris Sutton working on obtaining LEED credentials